## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass |  | Pass |  | Pass
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass |  | Pass |  | Pass
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass |  | Pass |  | Pass
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass |  | Pass |  | Pass
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass |  | Pass |  | Pass
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass |  | Pass |  | Pass
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass |  | Pass |  | Pass
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass |  | Pass |  | Fail | Couldn’t pass or fail it as it does not have this functionality.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. | Fail | MA,RT,ST,PG,AN 10/10/2021 - This feature was not implemented correctly, the user did not get dragged in whatsoever. It would be buggy, we had the code trying to implement it, but it did not work. | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Fail | MA,RT,ST,PG,AN 10/10/2021 - We have had the ability to hover over a checker and be able to drag it, highlighting the image as well. But dragging the image image did not move it at all. | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Fail | MA,RT,ST,PG,AN 10/10/2021 - We have had the ability to hover over a checker and be able to drag it, highlighting the image as well. But dragging the image image did not move it at all. | Pass |  | Fail | Dropping on the same spot throws an error
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story, the drop action should not do anything; piece movement will be the focus of future stories. | Fail | MA,RT,ST,PG,AN 10/10/2021 - We have had the ability to hover over a checker and be able to drag it, highlighting the image as well. But dragging the image image did not move it at all. | Pass |  | Pass
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Fail | MA,RT,ST,PG,AN 10/10/2021 - We had an error where the peices were nto inverted for each user, but had the code trying to reflect it on each part. | Pass |  | Pass
As a Player, I want the game to end whenever there is a winner. | Given that a game has ended when I win a game then I expect to see an indication that I have won the game. |  |  | Pass |  | Fail | Game ended with both players having people on the board
| Given that a game has ended when I lose a game then I expect to see an indication that I have lost the game. |  |  | Pass |  | Fail | Game ended with both players having people on the board
| Given that my opponent resigned when the server posts then I expect to see that I won, and my opponent resigned. |  |  | Pass |  | Pass
| Given that I resigned when the server posts then I expect to see that I lost because I resigned. |  |  | Pass |  | Pass
| Given that the game ended when the game view updates then I expect to see only the EXIT button light up. |  |  | Pass |  | Pass
| Given that the game ended when I click EXIT then I expect to be redirected to the home page. |  |  | Pass |  | Pass
As a Player, I want to make legal moves, so that I don’t inadvertently violate the rules. | Given it is my turn when I make a valid move then I expect the move to work. |  |  | Pass |  | Pass
| Given it is my turn when I make an invalid move then I expect an error message indicating my move is invalid. |  |  | Pass |  | Pass
| Given there is no possible jump move when I make a simple move then I expect the move to work. |  |  | Pass |  | Pass
| Given there is a possible jump move when I don't make that jump move then I expect to receive an error message. |  |  | Pass |  | Pass
| Given it is my turn when I make a jump move then I expect to capture the opponent's piece. |  |  | Pass |  | Pass
| Given I play a king piece when I make a diagonally backward move then I expect the move to work. |  |  | Pass |  | Pass
| Given it is my turn when I click Back Up Move then I expect my move to reset. |  |  | Pass |  | Pass
| Given it is my turn when I click Submit Turn then I expect my move to be submitted. |  |  | Pass |  | Pass
As a Player, I want to play a King Checker whenever it reaches the furthest row. | Given it is my turn when a checker piece reaches the furthest row on the board then I expect my regular piece to change into a king piece. |  |  | Pass |  | Pass
As a Player, I want to know where the button to resign is, so I can give up whenever I want. | Given that I'm playing a game when I click the resign button then I expect the game to end. |  |  | Pass |  | Pass
As a Player, I want to confirm if I want to resign, so that I don’t accidentally give up. | Given that I am in a game when I click the resign button then I expect to see a confirmation prompt. |  |  | Pass |  | Pass
| Given that the confirmation prompt has shown up when I confirm that I want to resign then I expect the game to end. |  |  | Pass |  | Pass
| Given that the confirmation prompt has shown up when I confirm that I do not want to resign then I expect the game to continue. |  |  | Pass |  | Pass